## Project Planner
Project Planner
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 60 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
MEMBER | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Bautista | priority scheduling | 10 | 7 | 0 | 0 | 0%
| test priority sheduling | 17 | 2 | 0 | 0 | 0%
| mod ifypriority scheduling | 19 | 8 | 0 | 0 | 0%
| set priority | 27 | 7 | 0 | 0 | 0%
| test set priority | 34 | 6 | 0 | 0 | 0%
Rayco | priority scheduling | 10 | 7 | 0 | 0 | 0%
| test priority sheduling | 17 | 2 | 0 | 0 | 0%
| modify priority scheduling | 19 | 8 | 0 | 0 | 0%
| get priority | 27 | 7 | 0 | 0 | 0%
| test get priority | 34 | 6 | 0 | 0 | 0%
Sigua | priority scheduling | 10 | 7 | 0 | 0 | 0%
| test priority sheduling | 17 | 2 | 0 | 0 | 0%
| merge commits | 19 | 1 | 0 | 0 | 0%
| modify priority scheduling | 20 | 8 | 0 | 0 | 0%
| priority donation | 28 | 7 | 0 | 0 | 0%
| test priority donation | 35 | 3 | 0 | 0 | 0%